## Sheet 1 - WOMENSwear Marketing
WOMENSwear Marketing Chart
Activity Date W/C | Event Date | Event | Marketing Mix Element | Target Group | Specific Marketing Activity | Who | Status | Notes
21.02.15 | 19.05.15 | Womenswear | Social Media | Online- students, general public, social media users. | Promotion of the show on Twitter, Facebook, the blog. | Lauren, Holly, Sam | Ongoing
02.03.15 | 19.05.15 | Womenswear | Social Media | Online- students, general public. | Promotion of online survey | Lauren, Sam, Holly | Ongoing
02.03.15 | 19.05.15 | Womenswear | Social Media | Online- students, general public, social media users. | Video blog post on Facebook | Lauren | Complete
02.03.15 | 19.05.15 | Womenswear | Social Media | Online- students, general public, social media users. | Create a Facebook event | Sam | Complete
16.03.15 | 19.05.15 | Womenswear | Social Media | Online- students, general public, social media users. | Release promotional image for show | Lauren | Complete
13.04.15 | 19.05.15 | Womenswear | Flyers/ posters | Students, general public, LPAC visitors, on campus | Order flyers (A6)/ posters (A3) | Lauren and Holly | Complete | Order from Instantprint.
13.04.15 | 19.05.15 | Womenswear | T shirts | Students, general public, on campus | Order t shirts | Lauren and Holly | Cancelled | Contact printing company
20.04.15 | 19.05.15 | Womenswear | Posters | Visitors to LPAC/ cafes and bars in Lincoln | Posters up in LPAC/ other cafes and bars | Lauren/ LPAC FOH Staff | Complete | Lauren to contact FOH staff and cafes in Lincoln when posters arrive
20.14.15 | 19.05.15 | Womenswear | Flyers | Visitors to LPAC/ cafes and bars in Lincoln | Flyers in LPAC/ cafes and bars | Lauren/ LPAC FOH Staff | Complete | Lauren to contact FOH staff and cafes in Lincoln when flyers arrive
27.04.15 | 19.05.15 | Womenswear | Distribution | Crouch, Touch, Pause Engage audience members | Exit flyer Out of Joint show 01.05.15 | Lauren/ LPAC FOH Staff/ Julie | Complete | Lauren to email Julie
27.04.15 | 19.05.15 | Womenswear | Email | Students/ alternative theatre-type audience | Blackboard/ LPAC email system | Lauren/ Julie | Complete | Lauren to liase with Julie
04.05.15 | 19.05.15 | Womenswear | Press | General public | Press release sent out | Lauren | Complete | Write and send press release to newspapers
04.05.15 | 19.05.15 | Womenswear | Press | General public | Radio- Siren FM | Lauren | Pending | Contact Siren FM to talk about show on air
04.05.15 | 19.05.15 | Womenswear | Distribution | Students/ general public | Flyering | Lauren, Holly, Sam | Complete | Flyering event in town/ on campus
11.05.15 | 19.05.15 | Womenswear | Distribution | Students/ general public | Flyering | Lauren, Holly, Sam | Complete | Flyering event in town/ on campus